## Slide 1: ORIENTATION OF ASSISTANT ENGINEERS
CONTRACT MANAGEMENT
BY
ING. FRANKLIN A. AGBANATOR
KOFORIDUA TRAINING CENTRE
(KTC)
1ST – 3RD OCTOBER 2018

## Slide 2: Introduction
The art (or science) of managing resources is complex
It is more complex and risky when it relates to construction contracts which have their peculiar problems.
The environment (social, economic and sometimes political) in which contracts are executed also adds to the complexity of managing contracts.

## Slide 3: Introduction (Cont;d)
The probability that things will go a bit awry with legal and, of course, financial implications is quite high in construction contracts in view of the many uncertainties associated with them.
It is therefore, very essential that the management of construction contracts is addressed very professionally.

## Slide 4: Contract Documents
Contract documents are prepared to provide enabling environment for the effective contract management. Contracts are managed through the provisions made in the contract documents so as to minimize subjectivity.

## Slide 5: Contract Documents (Cont;d)
A contract document may be defined as a tender document with the blanks filled in and the Form of Agreement signed by the parties to the contract.
The contract document for works contracts comprise the following arranged in the order of preference:-

## Slide 6: Contract Documents (Cont;d)
Form of agreement
Letter of acceptance
Form of tender and appendix thereto
Special conditions of contract

## Slide 7: Contract Documents (Cont;d)
General conditions of contract
Technical specifications
Drawings
Bill of quantities
Other documents

## Slide 8: Contract Documents (Cont;d)
Contract documents for services comprise the following:-
Contract agreement
Notification of award
Letter of invitation
Terms of reference
Supplementary information
Schedule of work and personnel
Bills of quantities
Other documents

## Slide 9: RESPONSIBILITIES OF PARTIES UNDER FIDIC CONDITIONS OF CONTRACT FOR WORKS
The main parties to a contract are the Employer and the Contractor. However under FIDIC the Engineer plays key roles on behalf of the employer. The roles of the three key players are, therefore, outlined as:

## Slide 10: ROLES OF THE EMPLOYER / CONTRACT MANAGER
a) Sound project preparation
b) Preparation of Tender documents
c) Prequalification of Tenderers, if required
d) Opening and Evaluation of Tenders
e) Award of contracts
0 Create supervision organization
g) Implement the contract (Payment, Approvals, etc.)
h) Take Over and ensure care of the works

## Slide 11: Role of Engineer/Contract Manager
  reviewing and updating design details;
  monitoring contractor's operations to ensure timely commencement of operation;
  reviewing contractor's programme;
  carrying out quality control tests;
  reviewing contractor's monthly invoices and certifying for payment;
  evaluating all claims for additional payment and applications for extension
  of time; and
  preparing monthly, quarterly and annual progress reports.

## Slide 12: SPECIFIC IMPORTANT ACTIVITIES
Six (6) very important activities are performed by the Engineer Contract
Manager.
These are:
a. Site Instructions;
b. Meetings;
c. Record Keeping;
d. Monitoring/controlling;
e. Certification; and
f. Reporting.

## Slide 13: Monitoring and Controlling
Control aims at regular monitoring of achievement
against the planned
progress, In addition, the Manager must monitor for quality control through
examination and testing of materials,

## Slide 14: Certification
The Manager certifies work done for payment and
also does the following
substantial completion and issue of taking over
certificate;
valuation of variations and Fixing of rates;
defects liability.

## Slide 15: PRICE ADJUSTMENT FORMULA (E)
HISTORY
The formula method seeks to calculate a sum or
sums, which will offer the
contracting parties adequate compensation for
losses caused by increase and decrease in costs.
The method does not, however, aim to access the exact amount of loss incurred.

## Slide 16: PRICE ADJUSTMENT FORMULA (E)
The basic concepts of the formula were introduced in 1971 by the Baxter commission in the U.K. 1(is a polynomial formula, which represents the best
estimate of the mix of, inputs (i.e. labour, plant,
materials etc.) in the
estimated cost of the contract.

## Slide 17: TERMINOLOGY
Base Indices: These are the cost indices or reference prices corresponding to each cost element i.e. Labour, plant, material etc., at the date specified under
the relevant clause of the conditions of contract
which shall be those prevailing on the day 28 days
prior to the closing date for the submission of bids

## Slide 18: TERMINOLOGY
Current Indices: These are those prevailing 28
days prior to the last day of the period to which a particular Interim Payment Certificate is related.

## Slide 19: Terminology
Provisional Indices: Where the published current
indices are not available at the time of preparing the
Interim Payment Certificate provisional indices as
determined by the Engineer can be applied subject
to subsequent correction when the firm indices are
available.

## Slide 20: Terminology
Proxy: Where the index for an item is not available, the equivalent index for a similar items (s) may be used (either by intra - or extra - polation).
This is called proxy index.

## Slide 21: Terminology
Adjustable Amount: This amount represents the estimated value of work carried out in a particular month or period determined in accordance with the relevant clauses of the contract.

## Slide 22: Terminology
Base Date (Month): This is the date (month) stated
in the Appendix to the Form of Bid from which the
adjustment is calculated i.e. 28 days prior to the
closing date for submission of bids.

## Slide 23: Terminology
Weightings (Coefficients): These represent the
estimated portions of each cost element such as
labour, materials, plant miscellaneous etc. in the works or sections thereof excluding provisional
sums. The aggregate of these coefficients for the
respective work section should be Unity (1)

## Slide 24: Terminology
Price Adjustment Factor (PAF): The PAF is the
factor derived from the polynomial by which the
Adjustable Amount is adjusted to produce the
fluctuation.

## Slide 25: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Provisional Sums: Provisional sums for works to be paid at current prices
e.g. by day works, statutory undertakers
are to be excluded from the work
categories and are therefore not subject
to adjustment.

## Slide 26: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
(b) Variation
(i) Additional works measured and priced at bill rates or analogous rates or at rates current at base date, arc subject to adjustment.
(ii) Additions which are valued at day work basis with current prices or at rates or prices current
at the dale of execution are excluded from the
adjustment.

## Slide 27: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Value of Materials on site: This is not the adjustable since they are priced at invoice rates. Moreover, only an agreed percentage i.e. 75% of the
value is incorporated in the payment certificate.
It only becomes adjustable when incorporated in
the works.

## Slide 28: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Payments to Nominated Sub-contractors and
Suppliers: Such payments including profits are not
adjustable when paid at current values. However,
attendance which is indicated as a sum is
adjustable.

## Slide 29: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Claims for Loss and / or Expense: Since these are normally assessed at full value, they are not
adjustable.
(f) Retention: Unlike the traditional method,
the amount of fluctuation derived by the formula
approach is subject to retention.

## Slide 30: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Work Executed After the Completion or Extended
Completion Date:
where an extension is granted with an express provision that it
is "without cost" to the Employer, only the
price adjustment factors applicable to the original
completion date, will apply.
In situations like this, the adjustment factor is computed using the indices or price relating to the prescribed time for
completion

## Slide 31: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Value of Work Included in Valuations Issued After Certificate of Practical Completion:
Such work may not be attributable to any valuation period, the value is
adjusted by:
Factor = Total Fluctuation Amount in Previous Certificates
Total value of work in Previous Certificates
It is therefore computed on the basis of average fluctuation over the contract period.

## Slide 32: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Errors: These may be classified as
(i) Mechanical and
(ii) Valuation Errors

## Slide 33: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Mechanical Errors: Possible errors here are:
a) Arithmetical errors in calculation of the
adjustment
b) Incorrect allocation of value to work
categories (sections)
c) Incorrect allocation of work such as specialist
work, and
d) Use of an incorrect index or indices.

## Slide 34: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Any such errors should be corrected It is required that in effecting the correction, the same indices should
be used as were used during the original calculations,
except that where firm indices are available they
should be substituted for provisional ones.

## Slide 35: BASIC PRINCIPLES RELATING TO THE APPLICATION OF THE FORMULA
Valuation Error: The general rule is that "valuations should be as
firm and accurate as possible as these will not normally be
reassessed at a later date".
However, the view is being held that where errors have been
committed, they should be corrected provided firm indices have not
yet been substituted
for provisional ones. It is further recommended that any further
correction after the application of the firm indices should be treated the same way as the value of work included in certificates after Practical completion.

## Slide 36: Use of a Correction Factor to the Indices:
Where for example an index is expressed in a currency other than the currency payable under the contract a correction factor, Z, is applied in order to avoid any distortions as a result of differential rates of price variations and periodic exchange rate changes

## Slide 37: METHOD OF MEASUREMENT
Provision for admeasurement of works is made under the relevant Clauses of the Conditions of Contract
They require that:
  works be re-measured
  joint measurements be made (Engineer/Contractor)
  particulars required by the Engineer be supplied by the Contractor.

## Slide 38: METHOD OF MEASUREMENT
Provisions require works to be measured net except where otherwise provided for in the contra
Civil Engineering works carried out by Ministry of
Roads and Highways of Ghana are measured in
accordance with the edition of the Civil Engineering
Standard Method of Measurement

## Slide 39: METHOD OF MEASUREMENT
Measurement (CESMM) specified in the Preambles to the Bill of Quantities. The Latest edition is
CESMM4. Consultants are advised to be conversant
with its provisions to avoid measurement related
disputes.

## Slide 40: CONCLUSION
Thorough documentation will enhance the successful management of contracts. Consultants must pay
attention to detail during project preparation and
documentation so as to ensure optimum project
delivery.

## Slide 41: THANK YOU